## TIME MANAGEME Gantt Chart BLANK
PROJECT TITLE | AI Trademark Logo Creator
PROJECT MANAGER | Khaw Teng Xian B031910447
GROUP MEMBERS | LIM WEN NI B031910441, RECA SENG BINTI MOHD FADZIL SENG B031910187
GROUP NAME | Hilton Technology
COMPANY NAME | Hilton Technology Sdn Bhd
DATE | 20/11/2021
GITHUB | https://github.com/tengxian4/AI-Trademark-Logo-Creator
TIME MANAGEMENT GANTT CHART
[AI Trademark Logo Creator]
| TASK NAME | START DATE | END DATE | DURATION (days)
| 1.0 Project Conception & Initiation | 2021-10-04 | 2021-10-08 | 5
| 1.1 Project Charter | 2021-10-05 | 2021-10-05 | 1
| 1.1.1 Sign the contract | 2021-10-05 | 2021-10-05 | 1
| 1.1.2 Statement of Work | 2021-10-05 | 2021-10-07 | 3
| 1.2 Stakeholders | 2021-10-05 | 2021-10-07 | 3
| 1.2.1 Meet with MyIPO (in our case we meet with Prof) | 2021-10-05 | 2021-10-06 | 2
| 1.2.2 Meet with users of the existing logo generator | 2021-10-07 | 2021-10-07 | 1
| 1.3 Develop preliminary project scope | 2021-10-07 | 2021-10-07 | 1
| 1.4 Research | 2021-10-05 | 2021-10-08 | 4
| 1.4.1 Research on Deep Learning | 2021-10-05 | 2021-10-08 | 4
| 1.4.2 Research on Image Processing | 2021-10-05 | 2021-10-08 | 4
| 1.4.3 Research on GPT3 | 2021-10-05 | 2021-10-08 | 4
| 1.5 Project Initiation | 2021-10-08 | 2021-10-08 | 1
| 2 Project Definition & Planning | 2021-10-11 | 2021-10-22 | 12
| 2.1 Collect Requirement | 2021-10-11 | 2021-10-13 | 3
| 2.1.1 Interview the users of the existing logo generator | 2021-10-11 | 2021-10-12 | 2
| 2.1.2 Observe logo designers in designing logo | 2021-10-11 | 2021-10-13 | 3
| 2.2 Define Scope | 2021-10-14 | 2021-10-15 | 2
| 2.2.1 Get expert judgement from Supervisor Quek Yao Jing | 2021-10-14 | 2021-10-14 | 1
| 2.2.2 Analyze the product of logo generator | 2021-10-15 | 2021-10-15 | 1
| 2.3 Create WBS | 2021-10-18 | 2021-10-18 | 1
| 2.4 Verify Scope | 2021-10-19 | 2021-10-19 | 1
| 2.5 Control Scope | 2021-10-20 | 2021-10-21 | 2
| 2.6 Plan Human Resource | 2021-10-20 | 2021-10-21 | 2
| 2.7 Cost Estimating | 2021-10-20 | 2021-10-22 | 3
| 2.7.1 Find suitable laptop by considering price and spec | 2021-10-20 | 2021-10-20 | 1
| 2.7.2 Find suitable GPU Server by considering price and spec | 2021-10-21 | 2021-10-21 | 1
| 2.7.3 Rough Order of Magnitude (ROM) Estimate | 2021-10-20 | 2021-10-22 | 3
| 2.8 Cost Budgeting | 2021-10-21 | 2021-10-22 | 2
| 2.9 Activity Define and Sequencing | 2021-10-21 | 2021-10-22 | 2
| 2.10 Develop Schedule | 2021-10-21 | 2021-10-22 | 2
| 2.11 Communication Plan | 2021-10-20 | 2021-10-22 | 3
| 2.12 Risk Management | 2021-10-20 | 2021-10-22 | 3
| 2.13 Collect Dataset | 2021-10-20 | 2021-10-22 | 3
| 2.14 Plan Procurement | 2021-10-22 | 2021-10-22 | 1
| 3 Project Launch & Execution | 2021-10-25 | 2021-12-03 | 40
| 3.1 Build responsibility Assignment Matrix | 2021-10-25 | 2021-10-26 | 2
| 3.2 Status & Tracking | 2021-10-25 | 2021-11-19 | 26
| 3.2.1 Train Models | 2021-10-25 | 2021-11-12 | 19
| 3.2.2 Model Selection | 2021-11-15 | 2021-11-19 | 5
| 3.2.3 Choose suitable Off the Shelf Software for Front-End | 2021-11-18 | 2021-11-18 | 1
| 3.2.4 Integrate the System with Front-End | 2021-11-18 | 2021-11-19 | 2
| 3.3 KPIs | 2021-11-22 | 2021-11-26 | 5
| 3.3.1 Monitoring | 2021-11-22 | 2021-11-26 | 5
| 3.3.2 Forecasts | 2021-11-24 | 2021-12-01 | 8
| 3.4 Validate Scope | 2021-11-26 | 2021-12-01 | 6
| 3.5 Control Scope | 2021-11-26 | 2021-12-01 | 6
| 3.5.1 Variance Analysis | 2021-11-26 | 2021-12-01 | 6
| 3.6 Project Updates | 2021-11-24 | 2021-12-03 | 10
| 3.6.1 Chart Updates | 2021-11-29 | 2021-12-03 | 5
| 3.6.2 Manage Project Team | 2021-12-02 | 2021-12-03 | 2
| 3.7 Cost Control | 2021-10-25 | 2021-10-26 | 2
| 3.8 Conduct Procurement | 2021-10-25 | 2021-10-25 | 1
| 3.9 Communicate with stakeholders | 2021-12-01 | 2021-12-03 | 3
| 4 Project Performance / Monitoring | 2021-12-06 | 2021-12-16 | 11
| 4.1 Project Objectives | 2021-12-06 | 2021-12-08 | 3
| 4.2 Quality Control | 2021-12-06 | 2021-12-10 | 5
| 4.3 Effort & Cost Tracking | 2021-12-13 | 2021-12-16 | 4
| 4.4 Communicate with stakeholders about the performance | 2021-12-13 | 2021-12-16 | 4
| 4.5 Project Performance | 2021-12-14 | 2021-12-16 | 3
| 5 Closing | 2021-12-17 | 2021-12-22 | 6
| 5.1 Close Procurement | 2021-12-17 | 2021-12-19 | 3
| 5.2 Close Project | 2021-12-19 | 2021-12-22 | 4
MILESTONE 1: Project Approval
7/10/21
Confirm the project
MILESTONE 2: Requirement Analysis and Scope review
21/10/21
Understand the requirement
MILESTONE 3: Cost Estimating and Budgeting
22/10/21
MILESTONE 5:Deployment
16/12/21
The system is ready to use.
MILESTONE 4: Implementation
3/12/21
Model is ready to use